## CM CR Role
CM Role list for CRs
Review information provided by the change owner
Generate CR Number
Notify stakeholders
record updated
When complete, record disposition and 'close', 'cancel' or 'complete'
Archive CR and related documents
Complile required CR report (weekly ccb status, or monthly CR metric)

## CR Workflow
Initiator | CM | Contract Reviewer | CM | NASA Reviewer | CCB Chair | CM | Change Implementer | CM
Create | Verify | Review | Verify | Review | Review | Verify | Make Change | Get approval to close record
Record | Notify Contractor | Comment | Notify NASA | Approve | Approve | Notify Implementer
Plan |  | Approve |  | or Disapprove | or Disapprove