## Slide 1: Service Request Review Team (SRRT) Authorization to Develop Class 1 Service Request
Migrate Career Management Tracking System (CMTS) from the WESTPrime environment to the HQ VM Cluster
SR# 2015-0002618
Phase = SRRT
SR Requester = Chris McCoy
NASA Organization Name = Information Technology Communications Division (ITCD)
Priority = Routine
Task Order / Funding = 10.01
Deployment Date: 06/19/2015
ECD: 06/30/2015
Luis Ayala
06/03/2015

## Slide 2: System/Project Overview
System/Project Name: Career Management Tracking System (CMTS)
System/Project Owner: Deandrea Peters
Purpose of System/Project: Database for counselors to compile monthly statistics and maintain details of visits by HQ employees for career counseling and/or work life coaching, events and counselor activities. Allows Human Resources Management Division (HRMD) to track the management activities of two career counselors.
Current Version: 4.0
Proposed Version: 5.0
Resides: Cuomo (WESTPrime)
ACES Category: Existing Call List
Project Funding Status: Funded

## Slide 3: Requirements
Description of Work
  Customer Outreach – Notify app owner
    Determine if application is an archive candidate
  Prepare application for migration from the WESTPrime environment to the HQ VM Cluster
    Complete ESD Ticket - Request source code files and data from WESTPrime
    Complete WESTPrime JIRA Ticket - Request will include to lock the application database, on specific day and time of deployment.
  Move application source code files and configure access to current application data to Dev Stage VM Environment
    Verify current version is the same version in STACR using a DIFF file
    Perform necessary application analysis to ensure no code changes are required
    Configure SiteMinder
  Create Documentation
    Change Package Request
    Version Description Document (VDD)
    Update SSAC
    Update Architecture Diagram as required
    Update SDD as required
  Move application source code to Stage VM
    Perform DTRR to include developer testing in lieu of QA testing
    Perform Security high-level review
    Perform UAT

## Slide 4: Requirements Cont.
Description of Work
  Complete ORR and WESTPrime CCB
  Prepare application for migration to Production VM
    Application will be locked on Thursday at 6:00 pm per WESTPrime Jira Ticket
    Deployment to HQ VM Cluster will occur the following Friday morning
    Verify the successful deployment internally
    Notify application owner of deployment completion and to validate the deployment
    Notify ITCD with migration deployment customer validation

## Slide 5: Justification / Background
Customer Justification
  Since the HQ applications went to Operations and Maintenance status in the WestPrime environment, we have noted several inefficiencies and redundant processes that add to the cost of hosting the applications. In addition, with no access to monitoring tools for the environments, there is delayed notification of outages and difficulty with troubleshooting problems.
Background
  The Information Technology & Communications Division began data center consolidation to reduce the NHCC foot print. One aspect of this initiative is to host applications utilizing the cloud technology and minimizing the physical server inventory. Currently, ITCD has concerns of the stability of the WESTPrime environment. Specifically, there were post patching issues which caused unscheduled application outages and notifications for patching is not always timely.

## Slide 6: Hardware / Software Profile
 | Current State
Number of Users | 17
Software | 
Desktop | Standard Web Browsers
Server | ColdFusion 10, Redhat 6, Apache 2.2
Hardware | Cuomo
Environment | WESTPrime
 | Proposed State
Number of Users | 17
Software | 
Desktop | Standard Web Browsers
Server | ColdFusion 10, Redhat 6, Apache 2.2
Hardware | cmts.hq.nasa.gov
Environment | HQ VM Cluster

## Slide 7: Approach
Classification F – General Purpose computing software (Multi-Center)
Waivers/Exceptions
  Work started prior to SRRT per ITCD approval
  SRR/PDR/CDR Waived
  Q/A formal testing waived - Q/A testing will be performed by developer and Business Analyst
508 Review
  Not Required
Architectural Review Board (ARB)
  Not Required
  PMRB
  Overall approach will be presented to PMRB for approval

## Slide 8: Summary Project Schedule
Activity / Milestone | Scheduled | Actual | 
Concept Phase |  |  | 
SRRT | 06/03/2015 |  | 
Requirements Phase |  |  | 
Start Work | 05/12/2015 | 05/12/2015 | 
SRR | Waived | Waived | 
Design/Development Phase |  |  | 
Security Self Assessment Check List (SSAC) |  |  | 
PDR | Waived | Waived | 
ARB KDP | Waived | Waived | 
CDR | Waived | Waived | 
DTRR (Staging) | 05/28/2015 | 05/28/2015 | 
Verification & Validation Phase |  |  | 
Security Testing | 06/02/2015 |  | 
QA Testing | Waived |  | 
TRR | 06/04/2015 |  | 
Security Review | 06/03/2015 |  | 
Deployment Phase |  |  | 
ORR | 06/17/2015 |  | 
WESTPrime CCB | 06/17/2015 |  | 
Security Plan | 06/18/2015 |  | 
ECD | 06/30/2015 |  | 

## Slide 9: ROM Estimate - Resources

## Slide 10: Project Contingency Factors
Assumptions
No application codes changes are required for the migration from WESTPrime to the HQ VM Cluster
WESTPrime will provide the source code files and application data
WESTPrime will lock down the application when required for deployment requirement
Daytime deployment authorized
Constraints
WESTPrime CCB schedule
Dependencies
WESTPrime CCB approval
WESTPrime support
Deviations
SRR/PDR/CDR Waived
Q/A will be performed by the development team and business analyst
508 not required
ARB not required
Issues
None
Notes: SLIDE PURPOSE: To communicate the major project issues
INSTRUCTIONS:
For the Issue Table, issues will be entered in rank from highest to lowest. For each row:
1. Click on the (Text) field in the Issue column and enter a summary statement of the issue.
2. Click on the (Text) field in the Action column and enter a summary of actions that have been or are to be taken to resolve the issue.
3. In the status column use the examples shown (optional) to indicate correct status for each issue.
4. In the Requested Assistance column, click on the (Text) field for any status shown as red or yellow and note the request for assistance in addressing the issue. If no assistance is requested, enter “NONE” in this column.
Issue Guidance for this report:
To contrast an issue vs. risk: A risk is something that may happen and if it does, will have an adverse impact on the project. Risk statements use If….. Then…. Logic. "That may happen" implies a probability of less then <100% and a risk must also have a probability of something above >0%. In reality, an issue/problem is an event that has already occurred..
The DoD Risk Management Guide for Acquisition contrasts risks and issues:
Issue: A problem or consequence which has occurred due to the realization of a root cause. A current issue was likely a risk in the past that was ignored or not successfully mitigated.
Risk: A measure of future uncertainties in achieving program performance goals within defined cost and schedule constraints. It has three components: a future root cause, a likelihood assessed at the present time of that future root cause occurring, and the consequence of that future occurrence.

## Slide 11
Project Risks
Risk ID | Trend | Risk | Mitigation
 |  | If additional time is needed for each application migration, HITSS will evaluate, provide LOE and cost difference for approval before proceeding. | HITSS will analyze each application and provide a new LOE when applicable.
 |  | Security Remediation – Security Remediation may require more effort than planned. | HITSS will closely monitor any issues and notify ITCD immediately if a modification of the schedule is necessary to accommodate any delays.
 |  | After the SiteMinder configuration changes some applications did not work as expected and required additional code changes. | All code changes will be briefed to ITCD and analysis and LOE will be provided.
1
2
Likelihood | 5 |  |  |  |  | 
 | 4 |  |  |  |  | 
 | 3 |  |  |  |  | 
 | 2 |  |  |  |  | 
 | 1 |  |  |  |  | 
 |  | 1 | 2 | 3 | 4 | 5
 |  | Consequence |  |  |  | 
2
!
Impact = Consequence x Likelihood
1
Project Risks Trend Legend |  |  |  |  |  |  |  |  | 
 | Decreasing (Improving) |  | Increasing (Worsening) |  | Unchanged |  | New Risk |  | Resolved
!
!
3
3
!

## Slide 12: Recommendation
Grant Authorization to Proceed (ATP) with the HQ VM Cluster migration efforts for CMTS, version 5.0 based on preceding explanation and proposed plan.