## Slide 1
HITSS CRs Implemented as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
2017-00155 Deploy NVDB v6.2.1 | Impacted Items: See CR for list | Deploy NVDB v6.2.1 | Initiated: 10/18/2017 Proposed: 11/14/2017 Closed: 11/14/2017
2017-00159 Decommission hqvault01.hq.nasa.gov | Impacted Items: See CR for list | Decommission hqvault01.hq.nasa.gov | Initiated: 9/7/2017 Proposed: 10/30/017 Closed: 11/15/2017

## Slide 2
ACES CRs Implemented as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
None This Week |  |  | 

## Slide 3
NICS CRs Implemented as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
2017-00152 JPL/HQ Wireless | Impacted Items: See CR for list | Add and permit 4 WLCs (3 production and 1 test) for JPL Wireless | Initiated: 10/13/2017 Proposed: 10/27/2017 Closed: 11/13/2017

## Slide 4
CRs Cancelled as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
None This Week |  |  | 

## Slide 5
HITSS CRs In Progress as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
2017-00142 Deploy sec-scan-tools.hq.nasa.gov | Impacted Items: See CR for list | Deploy sec-scan-tools.hq.nasa.gov | Initiated: 9/21/2017 Proposed: 10/5/2017 Approved: 10/5/2017
2017-00153 Address Issue with NEAR in Production | Impacted Items: See CR for list | Address Issue with NEAR in Production. | Initiated: 10/16/2017 Proposed: 10/30/2017 Approved: 11/7/2017
2017-00157 FW Change to allow public and agency network to reach github.hq.aws.nasa.gov | Impacted Items: See CR for list | FW Change to allow public and agency network to reach github.hq.aws.nasa.gov | Initiated: 10/26/2017 Proposed: 11/9/2017 Approved: 11/7/2017
2017-00160 Allow HTTPS access to MCE over new VPN profile | Impacted Items: See CR for list | Allow HTTPS access to MCE over new VPN profile | Initiated: 11/1/2017 Proposed: 11/1/2017 Contractor Review: 11/1/2017
2017-00163 Update cercla.hq.nasa.gov | Impacted Items: See CR for list | Update cercla.hq.nasa.gov | Initiated: 11/7/2017 Proposed: 11/21/017 NASA Review: 11/15/2017

## Slide 6
HITSS CRs In Progress as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
2017-00164 Address New DHS Cyberhygiene Findings | Impacted Items: See CR for list | Address New DHS Cyberhygiene Findings | Initiated: 11/7/2017 Proposed: 11/18/2017 Contractor Review: 11/7/2017
2017-00165 Deploy ITCD Web v3.1 | Impacted Items: See CR for list | Deploy ITCD Web v3.1 | Initiated: 11/1/2017 Proposed: 11/15/2017 CCB Chair: 11/15/2017
2017-00166 Windows Servers Patching for November 2017 | Impacted Items: See CR for list | Apply the latest Microsoft patches MS17- November Roll-up plus KB890830 Microsoft® Windows® Malicious Software Removal Tool on all Windows servers. | Initiated: 11/9/2017 Proposed: 12/2/2017 Contractor Review: 11/9/2017
2017-00167 Address security vulnerabilities for icts.hq.nasa.gov | Impacted Items: See CR for list | Address security vulnerabilities for icts.hq.nasa.gov | Initiated: 11/9/2017 Proposed: 12/2/2017 Contractor Review: 11/13/2017
2017-00168 Upgrade VMWare to 6.5u1 | Impacted Items: See CR for list | Upgrade VMWare to 6.5u1 | Initiated: 11/15/2017 Proposed: 11/29/2017 Contractor Review: 11/15/2017

## Slide 7
NICS CRs In Progress as of 11/15/2017
Change Request Status
NAME | CHANGE | DESCRIPTION | STATUS
2017-00156 Update ACLs on WLC for ClickShare | Impacted Items: See CR for list | This change is to modify the ACLs on the WLCs in order to permit ClickShare devices | Initiated: 10/24/2017 Proposed: 11/10/2017 NASA Review: 11/8/2017
2017-00161 Disable Unused WLAN SSIDs | Impacted Items: See CR for list | Disable unused SSIDs on HQ WLCs, nasa-atv and NASAHQ-eye-atv. These were used for Apple Airplay and Apple TV. These SSIDs are no longer used. | Initiated: 11/6/2017 Proposed: 11/24/2017 Contractor Review: 11/6/2017
2017-00162 Allow SMTP-Relay using Agency Mail Server | Impacted Items: See CR for list | Allow SMTP-Relay using Agency Mail Server | Initiated: 11/7/2017 Proposed: 11/24/2017 Contractor Review: 11/7/2017
2017-00169 Upgrade IOS on Switches from Concourse - 4th Floor | Impacted Items: See CR for list | Upgrade IOS on Switches from Concourse - 4th Floor | Initiated: 11/14/2017 Proposed: 12/1/2017 Contractor Review: 11/15/2017